## Campaign Brief
Campaign Details
Campaign Name | Q2 2026 Organic Growth Campaign
Website | quickseo.ai
Start Date | 2026-04-01
End Date | 2026-06-30
Campaign Manager
Budget | $5,000
Campaign Goals
Goal | KPI | Baseline | Target | Deadline
Increase organic traffic by 30% | Monthly organic sessions | 10,000 | 13,000 | 2026-06-30
Rank top 5 for 10 target keywords | Keywords in top 5 | 3 | 10 | 2026-06-30
Build 50 quality backlinks | Referring domains | 120 | 170 | 2026-06-30
Improve domain authority by 5 points | Domain authority score | 35 | 40 | 2026-09-30
Increase organic conversions by 20% | Monthly organic conversions | 200 | 240 | 2026-06-30
Created by QuickSEO — quickseo.ai

## Target Keywords
Keyword | Search Volume | Difficulty | Current Position | Target Position | Priority | Content Strategy | URL (Existing or Planned) | Status
seo campaign management | 2400 | 45 | 18 | 3 | Primary | Create comprehensive guide | /blog/seo-campaign-management | In Progress
seo campaign template | 1900 | 38 | 24 | 5 | Primary | Template landing page | /templates/seo-campaign | In Progress
how to plan seo campaign | 1600 | 42 | 32 | 5 | Primary | Step-by-step guide | /blog/how-to-plan-seo-campaign | Planned
seo strategy template | 3200 | 55 | 45 | 10 | Primary | Optimize existing page | /templates/seo-strategy | Not Started
keyword research process | 1200 | 40 | 28 | 8 | Secondary | Tutorial with examples | /blog/keyword-research-process | In Progress
link building strategy | 1800 | 52 | 35 | 10 | Secondary | Detailed how-to guide | /blog/link-building-strategy | Planned
content optimization checklist | 880 | 35 | 22 | 5 | Secondary | Downloadable checklist | /tools/content-optimization | Not Started
technical seo audit steps | 720 | 38 | 15 | 3 | Secondary | Update existing content | /blog/technical-seo-audit | In Progress
seo campaign tracking spreadsheet | 390 | 22 | 0 | 3 | Long-tail | Template download page | /templates/seo-campaign | In Progress
how to measure seo campaign success | 320 | 25 | 0 | 5 | Long-tail | Blog post with metrics | /blog/measure-seo-success | Planned
seo campaign report example | 260 | 20 | 0 | 3 | Long-tail | Example report page | /templates/seo-report | Not Started
quarterly seo campaign planning | 210 | 18 | 0 | 3 | Long-tail | Guide with templates | /blog/quarterly-seo-planning | Planned
Created by QuickSEO — quickseo.ai

## Content Plan
Content Piece | Target Keyword | Content Type | Word Count | Author | Draft Date | Publish Date | Promotion Channels | Status | URL
Complete Guide to SEO Campaign Management | seo campaign management | Guide | 3000 |  | 2026-04-01 | 2026-04-15 | Email, LinkedIn, Twitter | Planned | /blog/seo-campaign-management
How to Plan an SEO Campaign: Step by Step | how to plan seo campaign | Blog | 2000 |  | 2026-04-08 | 2026-04-20 | Email, Social Media | Planned | /blog/how-to-plan-seo-campaign
Keyword Research Process: A Practical Guide | keyword research process | Guide | 2500 |  | 2026-04-15 | 2026-04-28 | Email, LinkedIn | Not Started | /blog/keyword-research-process
Link Building Strategy for 2026 | link building strategy | Blog | 2200 |  | 2026-05-01 | 2026-05-12 | Email, Twitter, Reddit | Not Started | /blog/link-building-strategy
Content Optimization Checklist [Free Download] | content optimization checklist | Landing | 1500 |  | 2026-05-10 | 2026-05-20 | Email, Social Media | Not Started | /tools/content-optimization
How to Measure SEO Campaign Success | how to measure seo campaign success | Blog | 1800 |  | 2026-05-15 | 2026-05-28 | Email, LinkedIn | Not Started | /blog/measure-seo-success
SEO Campaign Report: What to Include | seo campaign report example | Blog | 1600 |  | 2026-06-01 | 2026-06-10 | Email, Social Media | Not Started | /templates/seo-report
Quarterly SEO Planning Guide | quarterly seo campaign planning | Guide | 2800 |  | 2026-06-10 | 2026-06-22 | Email, LinkedIn, Twitter | Not Started | /blog/quarterly-seo-planning
Created by QuickSEO — quickseo.ai

## Link Building Plan
Prospect Website | DA | Contact Person | Email | Outreach Type | Status | Link URL | Date
searchenginejournal.com | 92 | Editor |  | Guest Post | Identified
backlinko.com | 88 | Outreach Team |  | Resource | Identified
ahrefs.com/blog | 91 | Content Manager |  | Guest Post | Contacted |  | 2026-04-05
moz.com/blog | 93 | Editor |  | Resource | Contacted |  | 2026-04-08
neilpatel.com | 86 | Content Team |  | Skyscraper | Identified
semrush.com/blog | 89 | Editor |  | Guest Post | Negotiating |  | 2026-04-12
hubspot.com/blog | 94 | Blog Editor |  | Resource | Contacted |  | 2026-04-15
contentmarketinginstitute.com | 85 | Managing Editor |  | Guest Post | Published | https://example.com/post | 2026-03-20
searchengineland.com | 90 | Editor |  | HARO | Identified
yoast.com/blog | 82 | Content Manager |  | Broken Link | Contacted |  | 2026-04-18
Created by QuickSEO — quickseo.ai

## Campaign Performance
Week | Organic Sessions | Rankings Improved | Content Published | Links Built | Tasks Completed | Notes
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Monthly Summary
Week | Organic Sessions | Rankings Improved | Content Published | Links Built | Tasks Completed | Notes
Month 1
Month 2
Month 3
Created by QuickSEO — quickseo.ai