## Project Dashboard
SEO Project Management Dashboard
Project Name: | [Enter Project Name]
Client: | [Enter Client Name]
Website: | [Enter Website URL]
Project Manager: | [Enter PM Name]
Start Date: | [Enter Start Date]
Status Summary
Total Tasks | 20
Completed | 4
In Progress | 6
Blocked | 2
Not Started | 8
Completion % | 20%
Phase Progress
Phase Name | Total Tasks | Completed | % Complete | Status
Planning | 4 | 3 | 75% | On Track
Technical SEO | 5 | 1 | 20% | In Progress
Content | 5 | 0 | 0% | Not Started
Link Building | 3 | 0 | 0% | Not Started
Reporting | 3 | 0 | 0% | Not Started
Created by QuickSEO — quickseo.ai

## Task Board
Task ID | Task Name | Phase | Priority | Assigned To | Start Date | Due Date | Estimated Hours | Actual Hours | Status | Dependencies | Notes
T-001 | Define project scope & goals | Planning | P1 | Sarah Chen | 2026-03-16 | 2026-03-18 | 4 | 4 | Done | — | Approved by client
T-002 | Keyword research & mapping | Planning | P1 | James Wilson | 2026-03-16 | 2026-03-20 | 8 | 7 | Done | — | 150 keywords identified
T-003 | Competitor analysis | Planning | P1 | Sarah Chen | 2026-03-18 | 2026-03-22 | 6 | 6 | Done | T-001 | Top 5 competitors analyzed
T-004 | Create content calendar | Planning | P2 | Emma Davis | 2026-03-20 | 2026-03-25 | 4 | 3 | Done | T-002 | Q2 calendar ready
T-005 | Site crawl & technical audit | Technical SEO | P1 | James Wilson | 2026-03-23 | 2026-03-27 | 8 | 5 | In Progress | T-001 | Using Screaming Frog
T-006 | Fix crawl errors & broken links | Technical SEO | P1 | James Wilson | 2026-03-27 | 2026-04-02 | 6 | 0 | To Do | T-005 | —
T-007 | Optimize Core Web Vitals | Technical SEO | P2 | Alex Kim | 2026-03-27 | 2026-04-05 | 10 | 3 | In Progress | T-005 | LCP needs improvement
T-008 | Schema markup implementation | Technical SEO | P2 | Alex Kim | 2026-04-01 | 2026-04-08 | 8 | 0 | Backlog | T-005 | FAQ & product schema
T-009 | XML sitemap optimization | Technical SEO | P3 | James Wilson | 2026-04-02 | 2026-04-05 | 3 | 0 | Backlog | T-005 | —
T-010 | Write pillar page: SEO Guide | Content | P1 | Emma Davis | 2026-04-01 | 2026-04-10 | 12 | 0 | In Progress | T-002 | 3000+ words target
T-011 | Write cluster article 1 | Content | P2 | Emma Davis | 2026-04-07 | 2026-04-12 | 6 | 0 | To Do | T-010 | —
T-012 | Write cluster article 2 | Content | P2 | Emma Davis | 2026-04-10 | 2026-04-15 | 6 | 0 | To Do | T-010 | —
T-013 | Optimize existing top 10 pages | Content | P1 | Sarah Chen | 2026-04-01 | 2026-04-10 | 8 | 0 | In Progress | T-002 | Title tags & meta descriptions
T-014 | Internal linking optimization | Content | P2 | Sarah Chen | 2026-04-08 | 2026-04-15 | 5 | 0 | Backlog | T-010 | —
T-015 | Guest post outreach (10 sites) | Link Building | P1 | Alex Kim | 2026-04-07 | 2026-04-25 | 12 | 0 | Blocked | T-010 | Need pillar content first
T-016 | Broken link building campaign | Link Building | P2 | Alex Kim | 2026-04-15 | 2026-04-30 | 8 | 0 | Backlog | — | —
T-017 | HARO responses (weekly) | Link Building | P2 | Sarah Chen | 2026-04-01 | 2026-05-31 | 10 | 0 | In Progress | — | Ongoing weekly task
T-018 | Set up ranking tracking | Reporting | P1 | James Wilson | 2026-03-25 | 2026-03-28 | 4 | 2 | In Progress | T-002 | QuickSEO dashboard
T-019 | Create monthly report template | Reporting | P2 | Sarah Chen | 2026-04-01 | 2026-04-05 | 3 | 0 | Blocked | T-018 | Need tracking data first
T-020 | First monthly performance review | Reporting | P2 | Sarah Chen | 2026-04-28 | 2026-04-30 | 4 | 0 | Backlog | T-019 | —
Created by QuickSEO — quickseo.ai

## Team Workload
Team Member | Role | Tasks Assigned | Tasks Completed | Hours Estimated | Hours Logged | Utilization % | Current Tasks
Sarah Chen | SEO Lead | 6 | 2 | 30 | 13 | 43% | Competitor analysis, Optimize top pages, HARO responses
James Wilson | Technical SEO | 5 | 1 | 29 | 14 | 48% | Site crawl, Fix crawl errors, Ranking tracking
Emma Davis | Content Writer | 4 | 1 | 28 | 3 | 11% | Content calendar, Pillar page, Cluster articles
Alex Kim | Developer / Outreach | 4 | 0 | 38 | 3 | 8% | Core Web Vitals, Schema markup, Guest post outreach
Mike Torres | Project Manager | 1 | 0 | 4 | 2 | 50% | Monthly performance review
TOTAL | — | 20 | 4 | 129 | 35 | 27% | —
Created by QuickSEO — quickseo.ai

## Sprint Planning
Sprint # | Sprint Goal | Start Date | End Date | Tasks Planned | Tasks Completed | Velocity | Carry Over Items | Retrospective Notes
Sprint 1 | Project setup & planning | 2026-03-16 | 2026-03-29 | 5 | 4 | 22 hrs | T-005 (in progress) | Good kickoff, keyword research took longer than expected
Sprint 2 | Technical audit & content start | 2026-03-30 | 2026-04-12 | 6 | 0 | — | — | —
Sprint 3 | Content production & link building prep | 2026-04-13 | 2026-04-26 | 5 | 0 | — | — | —
Sprint 4 | Link building & content optimization | 2026-04-27 | 2026-05-10 | 4 | 0 | — | — | —
Sprint 5 | Ongoing optimization | 2026-05-11 | 2026-05-24 | 0 | 0 | — | — | —
Sprint 6 | Review & next quarter planning | 2026-05-25 | 2026-06-07 | 0 | 0 | — | — | —
Created by QuickSEO — quickseo.ai

## Meeting Notes & Decisions
Date | Meeting Type | Attendees | Key Discussion Points | Decisions Made | Action Items | Owner | Due Date
2026-03-16 | Client | Sarah, Mike, Client | Project kickoff, goals alignment, timeline review | Approved 12-week timeline, confirmed budget | Send project plan to client | Mike Torres | 2026-03-17
2026-03-17 | Standup | Sarah, James, Emma, Alex | Task assignments, tool access, priorities | James leads technical, Emma leads content | Set up Screaming Frog license | James Wilson | 2026-03-18
2026-03-20 | Weekly | Full team | Keyword research findings, competitor gaps | Target 50 primary keywords, 100 long-tail | Finalize keyword map | James Wilson | 2026-03-22
2026-03-23 | Standup | Sarah, James, Emma | Planning wrap-up, technical audit start | Begin crawl on Monday | Prepare crawl config | James Wilson | 2026-03-23
2026-03-27 | Weekly | Full team | Crawl results review, content calendar draft | Prioritize CWV fixes, approve Q2 calendar | Share crawl report with client | Sarah Chen | 2026-03-28
2026-03-29 | Retrospective | Full team | Sprint 1 review, velocity baseline | Set velocity target at 25 hrs/sprint | Update sprint 2 plan | Mike Torres | 2026-03-30
2026-04-03 | Client | Sarah, Mike, Client | Sprint 1 results, technical findings | Client approved technical fix priorities | Send technical audit summary | Sarah Chen | 2026-04-04
2026-04-06 | Standup | Sarah, James, Alex | CWV progress, schema planning | Start schema after CWV improvements ship | Draft schema requirements | Alex Kim | 2026-04-07
Created by QuickSEO — quickseo.ai